## Sheet1
SEVERITY
| Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level |  |  | Minimal | Minor | Moderate | Major | Severe
1 | Non Availablity of resources to complete task | Lack of Resources | From the design shouls be able to size resources | Ensure resources are available for dev and deployment | Unlikely | Major | 4 | LIKELIHOOD | Guaranteed | 5 | 10 | 15 | 20 | 25
2 | Lack of Techincal skill to complete project | Inadequate Training | Finish training | To be fully trained on technologies as and when required | Possible | Moderate | 6 |  | Expected | 4 | 8 | 12 | 16 | 20
3 | Late discovery of design flaw | Bad design | Early review of design | Best possible design inplace before attempting build | Possible | Moderate | 6 |  | Likely | 3 | 6 | 9 | 12 | 15
4 | Legal constraints assoicated with store Music data | Legal Contest | Check viability | To ensure that we have the legal right to the private storeage of data | Unlikely | Servere | 5 |  | Possible | 2 | 4 | 6 | 8 | 10
5 | System fails final user testing before release to users | Failed User testing | Ensure dev/unit/SIT testings are carried out correctlt | To ensure that the system works as designed | Possible | Moderate | 6 |  | Unlikely | 1 | 2 | 3 | 4 | 5
6 | System fails final smoke/pen test before release to users | Failed final testing | Ensure adherence to design principles relating to security | Ensure delivery is secured from external attack | Likely | Moderate | 9
7